## Sheet1
Sections | Bug Description | Bug Title | Steps to reproduce | Assigned to | Assigned by | Status | Priority | Environment | Comments
Home | Chat With Guru have very bad user experience | Chat With Guru have very bad user experience | 1 - Click on the "Ask anything to your guru" section 2 - Chat with your Guru |  | Soumya | Open | High | Prod
Home | The notification section displays a red notification indicator, suggesting that there are unread or new notifications. However, when the user opens the notification section, no new notifications are displayed. | Notification Badge (Red Dot) Appears Despite No New Notifications | 1 - Click on the notification badge |  | Soumya | Open | Medium | Prod
Home | When the user navigates to the Cart section, the page continues to display a loading indicator and does not load the cart contents, preventing the user from viewing or managing items in the cart. | Cart Page Keeps Loading Indefinitely | 1 - Click on the "My Cart" option |  | Soumya | Open | High | Prod
Home | When the user taps the Back button, the application exits completely instead of navigating back to the previous screen. If a previous screen exists in the navigation stack, the app should return to that screen rather than closing. | Application Closes Instead of Navigating to Previous Screen on Back Button Press | 1 - Navigate through the Reels section 2 - Tap the device or in-app Back button. |  | Soumya | Open | Medium | Prod
Faith | Both Heart and Super (hand gesture) reaction icons are displayed for the same action. Only one reaction type should be shown to avoid user confusion. | Duplicate Like Reaction Types Displayed | 1 - Open the Daiv app 2 - Check the "Explore Daiv Sevas" reels section (Hand gesture icon) 3 - Navigate to Faith 4 - Check the "Explore temple" section (Heart shape icon) |  | Soumya | Open | Low | Prod
Faith | When a user clicks the Super (hand gesture) reaction button on a post, the item is not being saved to the Favorites section. | Super Reaction (Hand Gesture) Not Added to Favorites | 1 - Open the Daiv app 2 - Navigate to Faith 3 - Check the "Explore temple" section (Heart shape icon) 4 - Navigate to Media 5 - Navigate to Videos 6 - Navigate to Favorite ( heart shape icon) option 7 - Verify the saved reels |  | Soumya | Open | High | Prod
Faith | After selecting a filter option in Temple Seva and saving it, the filtered content is displayed. However, when the user reopens the Temple Seva filter, the filter options and displayed content are not shown correctly. | Temple Seva Filter Options Not Displaying Correctly After Reopening | 1 - Open the Daiv app 2 - Click on the "Temple seva" option 3 - Click on any radio button and click on show result 4 - Verify the results 5 - Click on the seva option again 6 - Verify all the filter radio buttons |  | Soumya | Open | High | Prod
Faith | After selecting a filter option in Deities and saving it, the filtered content is displayed. However, when the user reopens the Deities filter, the filter options and displayed content are not shown correctly. | Deities Filter Options Not Displaying Correctly After Reopening | 1 - Open the Daiv app 2 - Click on the "Deities" option 3 - Click on any radio button and click on show result 4 - Verify the results 5 - Click on the Deities option again 6 - Verify all the filter radio buttons |  | Soumya | Open | High | Prod
Faith | When a user opens content from the Explore Temple section and likes it from the content detail page, the like is successfully applied. However, after returning to the Explore Temple section, the content does not show the updated liked state. | Like Status Not Updated in Explore Temple Section After Liking Content | 1 - Open the Daiv app 2 - Navigate to the Faith section 3 - Click on one content from "Explore Temples" section 4 - click on like icon inside the content 5 - Back to the previous page 6 - Verify the Favorite icon shuld be reflect for the respective content |  | Soumya | Open | Medium | Prod
Store | When a user clicks on any product in the Store section, the application navigates to a blank page instead of displaying the product details. | Product Click Redirects to Blank Page in Store Section | 1 - Open the Daiv app 2 - Navigate to "Faith" section 3 - Navigate to the "Store" section 4 - Verify the product |  | Soumya | Open | Low | Prod
Media | When a user creates a playlist in the Music section with a single input, two playlists are created instead of one. | Duplicate Playlist Created for Single User Input | 1 - Open Daiv app 2 - Navigate to the Media section 3 - Navigate to the Music section 4 - Create a playlist |  | Soumya | Open | High | Prod
Media | After creating a playlist in the Music section, the user is unable to perform further actions such as adding music, deleting the playlist, or managing playlist content. | Unable to Add, Delete, or Manage Playlist After Creation | 1 - Open Daiv app 2 - Navigate to the Media section 3 - Navigate to the Music section 4 - Create a playlist |  | Soumya | Open | Medium | Prod